# TERMS OF REFERENCE (TOR)

## DEVICE ASSESSMENT FOR 2027 ITN MASS CAMPAIGN

## 1. Background

During the 2023 ITN Mass Campaign, approximately 8,000 mobile devices were deployed to support data collection, registration, and operational activities.

As preparations begin for the 2027 ITN Mass Campaign, it is essential to assess the current condition of these devices to determine their usability, identify faults, and inform accurate procurement planning.

## 2. Goal of the Exercise

The goal of this exercise is to systematically assess 7,000 devices in order to:

- Determine the number of devices in good working condition

- Identify devices requiring repair or replacement

- Establish the procurement gap for 2027

- Optimize costs by maximizing reuse of functional devices

- Ensure only fully functional and updated devices are deployed

## 3. Objectives

- Conduct a comprehensive functional and physical assessment of all devices

- Classify devices as PASS (usable) or FAIL (not usable)

- Generate a verified inventory of devices

- Provide evidence-based procurement recommendations

## 4. Scope of Work

The assessment will include:

- Physical inspection of devices

- Functional testing (camera, touch, charging, etc.)

- Software updates and version verification

- Accessories testing (chargers, adaptors, USB cables)

- IMEI verification and documentation

- Final classification (PASS/FAIL)

## 5. Methodology

A 14-point checklist will be used for each device, covering:

- Camera/Scan

- Battery health

- Screen condition

- Software update

- Charger head (port)

- Adaptor

- Device charging

- Charging port check

- Adaptor re-check

- USB cord

- Touch responsiveness

- IMEI verification

- Phone case

- Packing completeness

Each device must pass all checks to be classified as PASS. Any failure results in FAIL, requiring repair or replacement.

## 6. Team Composition

- 35 Assessors (ICT4D Consultants)

- 7 Supervisors (1 supervisor per 5 assessors)

- 5 Support Labour Staff

## 7. Implementation Plan

- Each assessor processes 20 devices per day

- Daily output:
35 × 20 = 700 devices/day

- Duration: 10 working days

- Total devices assessed: 7,000

Supervisors will verify all assessed devices at the end of each day.

## 8. Daily Work Schedule (9:00 AM – 5:00 PM)

### Workday Structure

- Start: 9:00 AM

- End: 5:00 PM

- Morning Break: 30 minutes

- Lunch Break: 1 hour

- Afternoon Break: 30 minutes

### Detailed Workflow

9:00 AM – 9:18 AM (Active Assessment Block 1)

- Initial device checks:

  - Camera/Scan

  - Battery

  - Screen

  - Charger head

  - Adaptor

9:18 AM – 9:48 AM (Morning Break – 30 mins)

9:48 AM – 1:48 PM (Charging & Parallel Work – 4 hrs)

- Devices undergo:

  - Software update and Charging (4 hrs)

- Simultaneously, assessors continue:

  - Charging port check

  - USB cord check

  - Touch responsiveness

  - IMEI verification

  - Phone case inspection

  - Packing completeness

1:48 PM – 2:48 PM (Lunch Break – 1 hour)

2:48 PM – 4:00 PM (Active Assessment Block 2)

- Continue assessments

- Complete pending checks

- Prepare devices for validation

4:00 PM – 4:30 PM (Afternoon Break – 30 mins)

4:30 PM – 5:00 PM (Validation & Close of Day)

- Supervisors verify all devices

- Assign final status:

  - PASS (Ready)

  - FAIL (Repair/Replace)

- Daily reporting and sign-off

## 9. Deliverables

- Complete inventory of all assessed devices

- PASS/FAIL classification report

- Summary of functional devices

- List of faulty devices

- Procurement gap analysis

- Final assessment report

# 10. BUDGET – DEVICE ASSESSMENT FOR 2027 ITN MASS CAMPAIGN

| Category | Calculation | Total |
| --- | --- | --- |
| Personnel Cost (Assessors) | 35 assessors × 20 devices/day × $3/device × 10 days | $21,000 |
| Supervisors | 7 supervisors × $3/day × 10 days | $210 |
| Labour Support | 5 staff × $1/day × 10 days | $50 |
| Data Cost (Software Updates) | 35 assessors × $5/day × 10 days | $1,750 |
| GRAND TOTAL |  | $23,010 |

## 11. Duration

The exercise will be conducted over 10 working days.

## 12. Reporting

- Daily progress reports

- End-of-day supervisor validation logs

- Final comprehensive report including:

  - Device status summary

  - Key findings

  - Procurement recommendations

## 13. Final Outcome

At the end of this exercise, the program will have:

- A verified count of usable devices

- A clear repair and replacement plan

- Accurate procurement quantities for 2027

- A fully prepared and tested device pool for deployment